## AML Project plan
Alex Gorton | Alex G. |  |  |  | bring same scale, clean/remove noise.
Alex Bates | Alex B.
Siddharth Sengupta | Sid
Scott Tasker | Scott
Konstantin Orlovskiy | K
|  |  | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Deadline
PLAN 7/11 | Goals |  | 2019-11-10 | 2019-11-14 | 2019-11-17 | 2019-11-21 | 2019-11-24 | 2019-11-28 | 2019-12-01 | 2019-12-05 | 2019-12-08 | 2019-12-12 | 2019-12-15 | 2019-12-19 | 2019-12-22 | 2019-12-26 | 2019-12-29 | 2020-01-02 | 2020-01-05 | 2020-01-09 | 2020-01-12 | 2020-01-16 | 2020-01-19 16:00
Project Planning |  | (group) | bar: 2019-11-10 to 2019-11-14; 2019-11-21; 2019-12-29 to 2020-01-12
Pre-processing | cleaned file output. | Sid | bar: 2019-11-17; 2019-12-29
Selecting features | file with required features as output, there may be new features created. | Alex B. | bar: 2019-11-17 to 2019-11-21
Exploring and selecting ML algorithms |  | Alex G. | bar: 2019-11-17; 2019-11-24; 2020-01-05
Refining algorithms |  | K | bar: 2019-11-17; 2019-11-28; 2020-01-09
Evaluating model and analysing the results |  | Scott | bar: 2019-11-17; 2019-12-01; 2020-01-12
Future work / Discuss results |  | (group) | bar: 2020-01-16
Report 4,000 words (±10%) |  | (group) | bar: 2020-01-19 16:00
|  |  | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Sun | Thu | Deadline
PLAN 14/11 | Goals |  | 2019-11-10 | 2019-11-14 | 2019-11-17 | 2019-11-21 | 2019-11-24 | 2019-11-28 | 2019-12-01 | 2019-12-05 | 2019-12-08 | 2019-12-12 | 2019-12-15 | 2019-12-19 | 2019-12-22 | 2019-12-26 | 2019-12-29 | 2020-01-02 | 2020-01-05 | 2020-01-09 | 2020-01-12 | 2020-01-16 | 2020-01-19 16:00
Project Planning |  | (group) | bar: 2019-11-10 to 2019-11-14; 2019-12-05
Pre-processing | clean, scale | Sid | bar: 2019-11-17
Selecting features (reitareble) | file with required features as output, there may be new features created. For example, new indicator showing the speed of change in the data volume during last 5 min. | Alex B. | bar: 2019-11-17; 2019-11-24; 2019-12-08
Exploring and selecting ML algorithms |  | Alex G. | bar: 2019-11-17; 2019-11-28; 2019-12-12
Refining algorithms (reitareble) | train-train and train-validate datasets. Validation set should be of the size of test set. | K | bar: 2019-11-17; 2019-12-01; 2019-12-15
Evaluating model and analysing the results | test data set | Scott | bar: 2019-11-17; 2019-12-05; 2019-12-19
Future work / Discuss results |  | (group) | bar: 2019-12-19 to 2019-12-22
Report 4,000 words (±10%), ~700 words per section |  | (group) | 2020-01-09: ready